## 초급
ID | Task Name | Duration | Start | Finish | Predecessors | Resource Names | Setember |  |  |  |  | October | [8 empty] | November | [13 empty] | December
[7 empty] | 2020-09-01 | 2020-09-12 | 2020-09-16 | 2020-09-22 | 2020-09-24 | 2020-10-01 | 2020-10-02 | 2020-10-05 | 2020-10-08 | 2020-10-09 | 2020-10-10 | 2020-10-11 | 2020-10-16 | 2020-10-29 | 2020-11-01 | 2020-11-02 | 2020-11-04 | 2020-11-05 | 2020-11-07 | 2020-11-08 | 2020-11-09 | 2020-11-15 | 2020-11-17 | 2020-11-18 | 2020-11-20 | 2020-11-22 | 2020-11-23 | 2020-11-25 | 2020-12-02 | 2020-12-03 | 2020-12-04 | 2020-12-08
| Plan | 12 | 2020-09-01 | 2020-09-12 | bar: 2020-09-01 to 2020-09-12
1 | Idea and Bussiness Model Setting | 12 | 2020-09-01 | 2020-09-12 |  | 양희성, 박승현, 김동희, 유태훈
| Requirements Analysis | 31 | 2020-09-16 | 2020-10-16 | bar: 2020-09-16 to 2020-10-16
2 | Requirements Gathering and Definition | 17 | 2020-09-16 | 2020-10-02 |  | 양희성, 박승현, 김동희, 유태훈
3 | Functional Modeling(Use-case, BPM) | 9 | 2020-09-16 | 2020-09-24 |  | 양희성, 박승현, 김동희, 유태훈
4 | Use case descriptions | 11 | 2020-10-01 | 2020-10-11 |  | 양희성, 박승현, 김동희, 유태훈
5 | Structual Modeling(Class Diagram) | 8 | 2020-10-01 | 2020-10-08 |  | 양희성, 박승현, 김동희, 유태훈
6 | Behavior Modeling(Sequence, Communication, State) | 8 | 2020-10-09 | 2020-10-16 |  | 양희성, 박승현, 김동희, 유태훈
| Design | 24 | 2020-10-16 | 2020-11-08 | bar: 2020-10-16 to 2020-11-08
7 | Class Partitioning | 4 | 2020-10-29 | 2020-11-01 |  | 양희성, 박승현, 김동희, 유태훈
8 | System Architecture | 7 | 2020-11-02 | 2020-11-08 |  | 양희성, 박승현, 김동희, 유태훈
1
1
1
1
1
| Implementation | 62 | 2020-09-22 | 2020-11-22 | bar: 2020-09-22 to 2020-11-22
| Prototype | 10 | 2020-09-22 | 2020-10-01 | bar: 2020-09-22 to 2020-10-01
9 | AppRTC Video Streaming Prototype | 10 | 2020-09-22 | 2020-10-01 |  | 양희성
10 | Android User Interface Prototype | 10 | 2020-09-22 | 2020-10-01 |  | 박승현, 유태훈
11 | Firebase Authentication Prototype | 10 | 2020-09-22 | 2020-10-01 |  | 박승현, 유태훈
12 | Firebase Firestore Prototype | 10 | 2020-09-22 | 2020-10-01 |  | 김동희
| Version 01 | 49 | 2020-10-05 | 2020-11-22 | bar: 2020-10-05 to 2020-11-22
13 | Activity and GUI Implementation | 6 | 2020-10-05 | 2020-10-10 |  | 박승현, 유태훈, 양희성
14 | Inner AppRTC Integration | 7 | 2020-11-01 | 2020-11-07 |  | 양희성
15 | Firestore Mudule Implementation | 4 | 2020-11-01 | 2020-11-04 |  | 김동희
16 | Database based Information System Implementation | 4 | 2020-11-05 | 2020-11-08 |  | 김동희, 유태훈, 박승현
17 | Authentication Mudule Integration | 4 | 2020-11-01 | 2020-11-04 |  | 박승현, 유태훈
18 | Testing and Get Backlog | 15 | 2020-11-08 | 2020-11-22 |  | 양희성, 박승현, 김동희, 유태훈
| Requirements Analysis, Design | 15 | 2020-11-09 | 2020-11-23 | bar: 2020-11-09 to 2020-11-23
19 | Build First Sprint Backlog | 14 | 2020-11-09 | 2020-11-22 |  | 양희성, 박승현, 김동희, 유태훈
20 | Modify Requirements Definition | 3 | 2020-11-15 | 2020-11-17 |  | 양희성, 박승현, 김동희, 유태훈
21 | Modify and Add Functional Modeling | 3 | 2020-11-18 | 2020-11-20 |  | 양희성, 박승현, 김동희, 유태훈
22 | Modify and Add Structual Modeling | 3 | 2020-11-18 | 2020-11-20 |  | 양희성, 박승현, 김동희, 유태훈
23 | Modify and Add Behavior Modeling | 3 | 2020-11-18 | 2020-11-20 |  | 양희성, 박승현, 김동희, 유태훈
24 | Setting Project Design | 4 | 2020-11-20 | 2020-11-23 |  | 양희성, 박승현, 김동희, 유태훈
| Implementation | 16 | 2020-11-23 | 2020-12-08 | bar: 2020-11-23 to 2020-12-08
| Version 02 | 16 | 2020-11-23 | 2020-12-08 | bar: 2020-11-23 to 2020-12-08
25 | Additional activities and GUI implementation | 3 | 2020-11-23 | 2020-11-25 |  | 유태훈
26 | Implementation Prescription Encryption | 10 | 2020-11-23 | 2020-12-02 |  | 양희성, 유태훈
27 | Implementation Pharmacy System | 12 | 2020-11-23 | 2020-12-04 |  | 박승현, 김동희
28 | Implementation Fingerprint identification system | 11 | 2020-11-23 | 2020-12-03 |  | 양희성, 김동희
29 | Testing and Get Backlog | 5 | 2020-12-04 | 2020-12-08 |  | 양희성, 박승현, 김동희, 유태훈